## Gantt
Excel Grantt Chart - Time Schedule
1/ | Consultant's progress as per the RFP
[5 empty] | 2007-03-01 | [33 empty] | 2007-04-01 | [27 empty] | 2007-05-01
| Tasks | Days | Start | Finish | 2007-03-01 | [6 empty] | 2007-03-08 | [6 empty] | 2007-03-15 | [5 empty] | 2007-03-22 | [6 empty] | 2007-03-29 | [6 empty] | 2007-04-05 | [6 empty] | 2007-04-12 | [6 empty] | 2007-04-19 | [6 empty] | 2007-04-26 | [6 empty] | 2007-05-03 | [6 empty] | 2007-05-10 | [6 empty] | 2007-05-17 | [6 empty] | 2007-05-24 | [6 empty] | 2007-05-31
[5 empty] | 2007-03-01 | 39143 | 39144 | 39145 | 39146 | 39147 | 39148 | 39149 | 39150 | 39151 | 39152 | 39153 | 39154 | 39155 | 39156 | 39157 | 39158 | 39159 | 39160 | 39161 | 39162 | 39163 | 39164 | 39165 | 39166 | 39167 | 39168 | 39169 | 39170 | 39171 | 39172 | 39173 | 39174 | 39175 | 39176 | 39177 | 39178 | 39179 | 39180 | 39181 | 39182 | 39183 | 39184 | 39185 | 39186 | 39187 | 39188 | 39189 | 39190 | 39191 | 39192 | 39193 | 39194 | 39195 | 39196 | 39197 | 39198 | 39199 | 39200 | 39201 | 39202 | 39203 | 39204 | 39205 | 39206 | 39207 | 39208 | 39209 | 39210 | 39211 | 39212 | 39213 | 39214 | 39215 | 39216 | 39217 | 39218 | 39219 | 39220 | 39221 | 39222 | 39223 | 39224 | 39225 | 39226 | 39227 | 39228 | 39229 | 39230 | 39231 | 39232 | 39233 | 39234 | 39235 | 39236 | 39237 | 39238
Preliminary Concept Design of P001 |  |  | 2006-12-03 | 2007-05-10 | bar: 2007-03-01 2007-03-01 to 2007-05-10 39212
| Budget Approval for P001 by the client | 6 | 2006-12-03 | 2007-03-06 | bar: 2007-03-01 2007-03-01 to 2007-03-01 39147
| Issue request for full proposal to bidders | 1 | 2007-03-01 | 2007-03-01 | bar: 2007-03-01 2007-03-01
| Receive full proposals from bidders | 12 | 2007-03-02 | 2007-03-13 | bar: 2007-03-01 39143 to 2007-03-08 39154
| Evaluate proposals | 7 | 2007-03-14 | 2007-03-20 | bar: 2007-03-08 39155 to 2007-03-15 39161
| Negotiate & Award contract / LoA | 14 | 2007-03-21 | 2007-04-03 | bar: 2007-03-22 39162 to 2007-03-29 39175
| NTP for Engineering & Design | 1 | 2007-04-04 | 2007-04-04 | bar: 2007-04-05 39176
| Programming & Preliminary design concept | 30 | 2007-04-04 | 2007-05-03 | bar: 2007-04-05 39176 to 2007-05-03 39205
| Review & Approval of preliminary design concept | 7 | 2007-05-04 | 2007-05-10 | bar: 2007-05-03 39206 to 2007-05-10 39212
2/ | New requirement for the model
[5 empty] | 2007-03-01 | [33 empty] | 2007-04-01 | [27 empty] | 2007-05-01
| Tasks | Days | Start | Finish | 2007-03-01 2007-03-01: 2007-03-01; 2007-03-08 39149: 2007-03-08; 2007-03-15 39156: 2007-03-15; 2007-03-22 39162: 2007-03-22; 2007-03-29 39169: 2007-03-29; 2007-04-05 39176: 2007-04-05; 2007-04-12 39183: 2007-04-12; 2007-04-19 39190: 2007-04-19; 2007-04-26 39197: 2007-04-26; 2007-05-03 39204: 2007-05-03; 2007-05-10 39211: 2007-05-10; 2007-05-17 39218: 2007-05-17; 2007-05-24 39225: 2007-05-24; 2007-05-31 39232: 2007-05-31
Model & Video for P001 |  | 32 | 2007-03-31 | 2007-05-01 | bar: 2007-03-29 39172 to 2007-04-26 39203
| Manufacturing of the model | 28 | 2007-03-31 | 2007-04-27 | bar: 2007-03-29 39172 to 2007-04-26 39199
| Preparation of the fly through video | 28 | 2007-03-31 | 2007-04-27 | bar: 2007-03-29 39172 to 2007-04-26 39199
| Approval / transportation of Model & Video | 3 | 2007-04-28 | 2007-04-30 | bar: 2007-04-26 39200 to 2007-04-26 39202
| Public presentation of P001 | 1 | 2007-05-01 | 2007-05-01 | bar: 2007-04-26 39203
www.pro-eng.com
Modeling works have to start by 31-Mar-07 which is in 30 days from today.
Modeling works can start only after the preliminary concept design is finalized after 10-May-07.
- 40 days negative
01-May-07 Project Revealed